## Tasks
Target week | Wk | ID | Category | Task | Scope ref | Owner | Status | Priority | Depends on | Est (days) | Privacy check | Definition of done | Notes
Sep W1 | 1 | DAT-01 | Data | Entity-relationship diagram: student, enrolment, section, component, score | 8.2.2 |  | To do | P0 |  | 1 | No | Grading structure hangs off section, not student; reviewed by all three members
Sep W2 | 2 | DAT-02 | Data | Migration: core tables, keys and constraints | 8.3.2 |  | To do | P0 | DAT-01 | 1 | Yes | Migration runs clean on an empty database and is reversible
Sep W3 | 3 | PRV-01 | Privacy | Consent state in schema plus a guard on every write path | In scope 23 |  | To do | P0 | DAT-02 | 1 | Yes | No row is written for a student who has not granted storage consent
Sep W3 | 3 | DAT-11 | Data | Repository layer using parameterised queries only | 8.3.2 |  | To do | P0 | DAT-02 | 1 | Yes | No string-concatenated SQL anywhere in the repository
Sep W3 | 3 | DAT-03 | Data | Section grading structure storage (components, weights, mode, deadline) | In scope 1 |  | To do | P0 | DAT-02 | 1 | Yes | One section row carries the full structure; no per-student duplication
Sep W3 | 3 | DAT-09 | Data | Server-side weight-sum validation with explanatory rejection | In scope 7 |  | To do | P0 | DAT-03 | 0.5 | No | A structure summing to 95 percent is rejected with a message naming the gap
Sep W3 | 3 | DAT-04 | Data | Join-by-code: code generation, uniqueness, join operation | In scope 2 |  | To do | P0 | DAT-03 | 1 | Yes | Second account joins an existing section and sees the same structure
Sep W3 | 3 | API-03 | API | Course setup and join-by-code endpoints | In scope 1, 2 |  | To do | P0 | DAT-04, API-02 | 1 | Yes | Two accounts share one section through the API alone
Sep W3 | 3 | DAT-06 | Data | Score records against components | In scope 4 |  | To do | P0 | DAT-02 | 0.5 | Yes | A score cannot reference a component from another section
Sep W3 | 3 | DAT-07 | Data | Attendance records | In scope 5 |  | To do | P2 | DAT-02 | 0.5 | Yes | Attendance feeds the weighted score when the course weights it
Sep W3 | 3 | API-04 | API | Score and attendance endpoints | In scope 4, 5 |  | To do | P0 | DAT-06, API-02 | 1 | Yes | Scores post and read back correctly for the authenticated student only
Sep W3 | 3 | API-05 | API | Calculation endpoints: current score, required score, projection | In scope 9-13 |  | To do | P0 | ENG-05, API-02 | 1 | No | Every numeric field in the response comes from the engine, none computed in the route
Sep W3 | 3 | DAT-05 | Data | Cumulative GPA and credits-earned storage | In scope 3 |  | To do | P1 | DAT-02 | 0.5 | Yes | Values are per student and editable
Sep W3 | 3 | DAT-08 | Data | Repeat-enrolment record with previous grade | In scope 14 |  | To do | P1 | DAT-02 | 0.5 | Yes | Flag plus previous grade stored and readable by the GPAX path
Sep W3 | 3 | DAT-10 | Data | Cascade deletion of all data belonging to one student | In scope 27 |  | To do | P1 | DAT-02 | 0.5 | Yes | Deleting the student row leaves no orphan score, enrolment or consent row
Sep W1 | 1 | INF-01 | Infrastructure | Dockerfile and docker-compose (app, PostgreSQL, Tesseract) | 8.5.1 |  | To do | P0 |  | 1 | No | docker compose up gives a running API and an empty database on a teammate's machine
Sep W1 | 1 | INF-02 | Infrastructure | Deploy to Render or Railway with public HTTPS | 8.5.1 |  | To do | P0 | INF-01 | 1 | No | Public URL returns 200 on /health with a valid certificate
Sep W1 | 1 | INF-03 | Infrastructure | Environment variables and secret configuration | 8.5.2 |  | To do | P0 | INF-02 | 0.5 | Yes | No credential appears in the repository; app boots from env vars only
Sep W1 | 1 | LIN-01 | LINE | LINE channel and LIFF application registration | 8.5.2 |  | To do | P0 |  | 0.5 | No | Channel secret and access token available as environment variables
Sep W3 | 3 | LIN-02 | LINE | Webhook endpoint with HMAC-SHA256 signature verification over the raw body | 8.3.4 |  | To do | P0 | INF-02, LIN-01 | 1 | Yes | A request with a modified body is rejected before parsing
Sep W3 | 3 | LIN-03 | LINE | Return HTTP 200 immediately, process the event asynchronously | 8.3.4 |  | To do | P1 | LIN-02 | 0.5 | No | Webhook responds under one second regardless of downstream work
Sep W3 | 3 | INF-04 | Infrastructure | Migration runner wired into the deploy pipeline | 8.5.1 |  | To do | P1 | INF-02, DAT-02 | 0.5 | No | A push to main applies pending migrations before the new image serves traffic
Sep W1 | 1 | INF-06 | Infrastructure | Branch protection and mandatory PR review | 8.3.8 |  | To do | P1 |  | 0.25 | No | Direct pushes to main are rejected; one approval required
Sep W2 | 2 | INF-05 | Infrastructure | GitHub Actions running lint and Jest on every pull request | 8.3.8 |  | To do | P1 | ENG-02 | 0.5 | No | A PR with a failing engine test cannot be merged
Sep W1 | 1 | ENG-01 | Engine | Define engine public API: function signatures, input and output shapes | 7.2.1 |  | To do | P0 |  | 1 | No | Signatures documented and agreed; no function takes a database handle or a clock
Sep W1 | 1 | API-01 | API | REST contract: endpoints, methods, parameters, JSON responses | 8.2.4 |  | To do | P0 |  | 1 | No | Written and agreed before implementation so client and server can proceed in parallel
Sep W1 | 1 | UI-01 | Client | Figma wireframes for the seven core screens | 8.2.3 |  | To do | P0 |  | 1.5 | No | Consent, setup, join, score entry, OCR confirmation, course detail, GPAX comparison all drawn
Sep W2 | 2 | ENG-10 | Engine | Grade scale, letter thresholds and grade-point constants | 7.2.1 |  | To do | P0 | ENG-01 | 0.5 | No | Constants live in one module; no magic number appears elsewhere
Sep W2 | 2 | ENG-02 | Engine | Current weighted score per course | In scope 9 |  | To do | P0 | ENG-01 | 1 | No | Returns score and the weight actually graded so far; pure, no I/O
Sep W2 | 2 | ENG-03 | Engine | Minimum required score on remaining assessments | In scope 10 |  | To do | P0 | ENG-02 | 1 | No | Matches the RogerHub formula on three hand-checked cases
Sep W2 | 2 | ENG-04 | Engine | Target unreachability detection | In scope 11 |  | To do | P0 | ENG-03 | 0.5 | No | Returns unreachable when required score exceeds the maximum obtainable
Sep W2 | 2 | ENG-05 | Engine | Criterion-referenced letter grade projection | In scope 12 |  | To do | P0 | ENG-02, ENG-10 | 1 | No | Projects a letter only when the course is criterion-referenced
Sep W2 | 2 | ENG-06 | Engine | Norm-referenced branch: score only, no letter grade | In scope 13 |  | To do | P0 | ENG-05 | 0.5 | No | Returns a null letter with an explicit reason code, never a guess
Sep W2 | 2 | ENG-07 | Engine | GPAX projection from current GPA and credits earned | In scope 3, 16 |  | To do | P0 | ENG-01 | 1 | No | Reproduces a hand-calculated GPAX for a three-course scenario
Sep W2 | 2 | API-02 | API | Express skeleton: routing, request validation, error handling | 8.3.3 |  | To do | P0 | API-01 | 1 | No | Invalid payloads return a structured 400 rather than a stack trace
Sep W3 | 3 | ENG-09 | Engine | Stay versus withdraw comparison across grade scenarios | In scope 16, 17 |  | To do | P0 | ENG-07, ENG-05 | 1.5 | No | Returns both branches plus the delta; never returns a recommendation
Sep W3 | 3 | QA-01 | Verification | Engine unit tests covering the boundary cases | 8.4.1 |  | To do | P0 | ENG-09 | 2 | No | Zero-weight component, unreachable target, norm-referenced, weights not summing, repeated course all covered
Sep W3 | 3 | ENG-08 | Engine | Grade-replacement rule for repeated courses | In scope 15 |  | To do | P1 | ENG-07 | 1 | No | Returns the projected GPAX and the name of the rule applied
Sep W4 | 4 | API-06 | API | GPAX and stay-versus-withdraw endpoints | In scope 16, 17 |  | To do | P0 | ENG-09, API-02 | 1 | No | Response carries both branches and the disclaimer text field
Sep W4 | 4 | API-07 | API | Consent endpoints: grant, withdraw, delete account | In scope 23, 24, 27 |  | To do | P0 | DAT-10, API-02 | 1 | Yes | Storage consent and cross-border consent are separate flags with separate endpoints
Sep W4 | 4 | API-08 | API | LIFF ID token verification middleware | 8.3.5 |  | To do | P0 | API-02, LIN-01 | 1 | Yes | An expired or forged token is refused before any handler runs
Sep W4 | 4 | LIN-05 | LINE | Quick-reply score entry conversation flow | In scope 4 |  | To do | P0 | API-04, LIN-03 | 2 | Yes | A student records a score end to end without leaving the chat
Sep W4 | 4 | UI-02 | Client | React and Vite setup, LIFF SDK init, auth bootstrap | 8.3.5 |  | To do | P0 | LIN-01, API-08 | 1 | Yes | App opens inside LINE and identifies the student server-side
Sep W4 | 4 | OCR-04 | OCR | Manual grading-structure entry as a complete alternative path | In scope 8 |  | To do | P0 | UI-04 | 0.5 | Yes | A student can set up any course without ever using the camera
Sep W4 | 4 | LIN-04 | LINE | Rich Menu design and registration | In scope 28 |  | To do | P1 | LIN-01 | 1 | No | Menu appears in the chat and routes to the correct flow or LIFF screen
Sep W4 | 4 | UI-03 | Client | Course list and course detail screens | In scope 9 |  | To do | P1 | API-05, UI-02 | 1.5 | No | Shows current weighted score and required score per course
Sep W4 | 4 | UI-04 | Client | Grading structure setup and edit screen | In scope 1 |  | To do | P1 | API-03, UI-02 | 1.5 | Yes | Weights must sum to 100 before save is enabled; server still revalidates
Sep W4 | 4 | UI-05 | Client | Join-by-code screen | In scope 2 |  | To do | P1 | API-03, UI-02 | 0.5 | Yes | Wrong code produces a clear Thai error, not a blank screen
Sep W4 | 4 | UI-06 | Client | Score entry and attendance screens | In scope 4, 5 |  | To do | P1 | API-04, UI-02 | 1 | Yes | Entry from LIFF and entry from quick reply produce identical stored data
Oct W1 | 5 | UI-09 | Client | Disclaimer component bound to every comparison render | In scope 20 |  | To do | P0 | UI-07 | 0.5 | No | It is structurally impossible to render a comparison without the estimate-not-advice text
Oct W1 | 5 | UI-10 | Client | Two separate consent screens: storage, then cross-border transfer | In scope 23, 24 |  | To do | P0 | API-07, UI-02 | 1.5 | Yes | Declining the second still gives a fully working app; the two are never bundled into one tick box
Oct W1 | 5 | PRV-02 | Privacy | Cross-border consent flag routing explanation to template when declined | In scope 24, 25 |  | To do | P0 | EXP-01 | 0.5 | Yes | With the flag off, no request reaches the external service at all
Oct W1 | 5 | LIN-06 | LINE | Push notification sender | In scope 18 |  | To do | P1 | LIN-01 | 0.5 | Yes | A push reaches a test account
Oct W1 | 5 | LIN-07 | LINE | Deadline scheduler: unreachable target before withdrawal deadline triggers a push | In scope 18 |  | To do | P1 | ENG-04, LIN-06 | 1.5 | Yes | Job runs on a schedule, is idempotent, and never notifies the same student twice for one course
Oct W1 | 5 | UI-07 | Client | GPAX and withdrawal comparison view with Recharts | In scope 16, 17 |  | To do | P1 | API-06, UI-02 | 2 | No | Stay and withdraw branches shown side by side with the numeric delta
Oct W1 | 5 | UI-11 | Client | Account and data deletion screen | In scope 27 |  | To do | P1 | API-07, UI-02 | 0.5 | Yes | Deletion is user-initiated, confirmed, and irreversible
Oct W1 | 5 | UI-12 | Client | Thai copy and terminology pass across all screens | 3.8 |  | To do | P1 | UI-03 | 1 | No | One reviewer who did not write the screens reads every string for clarity
Oct W1 | 5 | EXP-01 | Explanation | Deterministic Thai template explanation generator | In scope 25 |  | To do | P1 | ENG-09 | 1.5 | No | Produces a complete, correct Thai explanation with the language model switched off
Oct W1 | 5 | EXP-02 | Explanation | Anonymised payload builder for the external service | In scope 26 |  | To do | P1 | ENG-09 | 0.5 | Yes | Payload contains no name, LINE user id, course id or individual component score
Oct W1 | 5 | QA-02 | Verification | Integration test: tampered webhook body is rejected | 8.4.2 |  | To do | P1 | LIN-02 | 0.5 | No | Test fails if signature verification is removed
Oct W1 | 5 | QA-03 | Verification | Integration test: expired ID token is refused | 8.4.2 |  | To do | P1 | API-08 | 0.5 | No | Test fails if verification is downgraded to decode-only
Oct W1 | 5 | UI-08 | Client | Non-GPAX withdrawal considerations panel | In scope 19 |  | To do | P2 | UI-07 | 0.5 | No | Lists lost credits, prerequisite dependencies, re-offering and fee implications
Oct W2 | 6 | QA-05 | Verification | System test of the full flow on the deployed instance | 8.4.3 |  | To do | P0 | UI-07, LIN-05 | 1 | No | Set up, join from a second account, record, calculate, receive notification, all on production
Oct W2 | 6 | PRV-03 | Privacy | PDPA data inventory: what is stored, why, where it goes, how it is deleted | 3.9, 3.10 |  | To do | P1 | DAT-01 | 1 | Yes | One page listing every stored field and its lawful basis, ready for the report
Oct W2 | 6 | QA-06 | Verification | UAT protocol: task list, observation sheet, consent for testers | 8.4.4 |  | To do | P1 |  | 1 | Yes | Written before testing so results are comparable across participants
Oct W2 | 6 | DOC-01 | Documentation | Architecture document and four-layer diagram | 8.2.1 |  | To do | P1 |  | 1 | No | Matches what was built, not what was proposed in August
Oct W2 | 6 | DOC-02 | Documentation | README and local setup instructions | 8.3.8 |  | To do | P1 | INF-01 | 0.5 | No | A teammate clones and runs the stack from the README alone
Oct W2 | 6 | OCR-01 | OCR | Tesseract in the container with Thai and English language data | In scope 6 |  | To do | P2 | INF-01 | 1 | No | Image never leaves the container; OCR runs with no outbound request
Oct W2 | 6 | OCR-02 | OCR | Syllabus table parsing into components and weights | In scope 6 |  | To do | P2 | OCR-01 | 2 | Yes | Extracts a usable draft from five real KKU syllabus photos
Oct W2 | 6 | OCR-03 | OCR | Mandatory confirmation and correction screen | In scope 6 |  | To do | P2 | OCR-02, UI-04 | 1 | Yes | Nothing extracted is stored until the student confirms or corrects it
Oct W2 | 6 | EXP-03 | Explanation | Gemini client with timeout and fallback to template | In scope 21 |  | To do | P2 | EXP-02, EXP-01 | 1 | Yes | A timeout or error silently falls back to the template, never to an empty reply
Oct W2 | 6 | EXP-04 | Explanation | Numeric verification of model output against the engine | In scope 22 |  | To do | P2 | EXP-03 | 1 | No | A deliberately altered number causes the response to be discarded and the template used
Oct W2 | 6 | QA-04 | Verification | Integration test: incorrect model number is discarded | 8.4.2 |  | To do | P2 | EXP-04 | 0.5 | No | Injected wrong number never reaches the student
Oct W3 | 7 | QA-07 | Verification | UAT sessions with 5 to 8 DME students and result recording | 8.4.4 |  | To do | P0 | QA-05, QA-06 | 2 | Yes | Per participant: which tasks completed unaided, and the step at which any failure occurred
Oct W4 | 8 | DOC-03 | Documentation | Final report | 9 |  | To do | P0 | QA-07 | 3 | No | Includes UAT results and an honest limitations section
Oct W4 | 8 | DOC-04 | Documentation | Demo video, 2 minutes or less | 9 |  | To do | P0 | QA-05 | 1 | No | Shows the full loop including the withdrawal comparison
Oct W4 | 8 | DOC-05 | Documentation | Presentation, 10 minutes or less | 9 |  | To do | P0 | DOC-03 | 1 | No | Rehearsed to time by all three members

## Summary
รอดมั้ย (Rord Mai?) task tracker
Every number here is a formula over the Tasks sheet. Do not type into it.
By week (same colours as column A of the Tasks sheet)
| Total | To do | Doing | Blocked | Done | % done | Est days | Days left
Sep W1 | 9 | 9 | 0 | 0 | 0 | 0% | 7.75 | 7.75
Sep W2 | 10 | 10 | 0 | 0 | 0 | 0% | 8 | 8
Sep W3 | 19 | 19 | 0 | 0 | 0 | 0% | 16.5 | 16.5
Sep W4 | 11 | 11 | 0 | 0 | 0 | 0% | 12 | 12
Oct W1 | 13 | 13 | 0 | 0 | 0 | 0% | 11.5 | 11.5
Oct W2 | 11 | 11 | 0 | 0 | 0 | 0% | 11 | 11
Oct W3 | 1 | 1 | 0 | 0 | 0 | 0% | 2 | 2
Oct W4 | 3 | 3 | 0 | 0 | 0 | 0% | 5 | 5
Total | 77 | 77 | 0 | 0 | 0 | 0% | 73.75 | 73.75
By priority
| Total | To do | Doing | Blocked | Done | % done | Est days | Days left
P0 | 43 | 43 | 0 | 0 | 0 | 0% | 44.5 | 44.5
P1 | 26 | 26 | 0 | 0 | 0 | 0% | 21.75 | 21.75
P2 | 8 | 8 | 0 | 0 | 0 | 0% | 7.5 | 7.5
Total | 77 | 77 | 0 | 0 | 0 | 0% | 73.75 | 73.75
By category
| Total | To do | Doing | Blocked | Done | % done | Est days | Days left
Infrastructure | 6 | 6 | 0 | 0 | 0 | 0% | 3.75 | 3.75
Engine | 10 | 10 | 0 | 0 | 0 | 0% | 9 | 9
Data | 11 | 11 | 0 | 0 | 0 | 0% | 8 | 8
API | 8 | 8 | 0 | 0 | 0 | 0% | 8 | 8
LINE | 7 | 7 | 0 | 0 | 0 | 0% | 7 | 7
Client | 12 | 12 | 0 | 0 | 0 | 0% | 13 | 13
OCR | 4 | 4 | 0 | 0 | 0 | 0% | 4.5 | 4.5
Explanation | 4 | 4 | 0 | 0 | 0 | 0% | 4 | 4
Privacy | 3 | 3 | 0 | 0 | 0 | 0% | 2.5 | 2.5
Verification | 7 | 7 | 0 | 0 | 0 | 0% | 7.5 | 7.5
Documentation | 5 | 5 | 0 | 0 | 0 | 0% | 6.5 | 6.5
Total | 77 | 77 | 0 | 0 | 0 | 0% | 73.75 | 73.75
By owner
| Total | To do | Doing | Blocked | Done | % done | Est days | Days left
Member 1 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
Member 2 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
Member 3 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
Total | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
Owner rows read names from the People sheet. Rename there, not here.
Capacity check: Days left per week should not exceed the team total on the People sheet.

## People
Name | Stream | Owns these categories | Capacity (days/week)
Member 1 | Core logic | Engine, Verification (unit), Explanation verification | 2
Member 2 | Platform | Data, API, LINE, Infrastructure, OCR backend | 2
Member 3 | Client | Client, Privacy screens, OCR confirmation, Documentation | 2
Team capacity per week |  |  | 6
Replace the placeholder names. The Owner dropdown on the Tasks sheet reads A2:A15. Capacity is person-days of real project work per week, not hours you hope to have.

## Legend
How to use
Palette | Sunny Beach Day, extended to eight steps. Cool teal at the start of the project, hot coral at submission.
Rows are sorted | Recommended platform implementation order first, followed by remaining tasks in their original order. Target weeks and priorities remain unchanged.
Edit these | Owner, Status and Notes. Their headers are the coral ones.
Do not edit | The Summary sheet. Every cell there is a formula counting the Tasks sheet.
Adding a task | Insert a row, give it an ID with the category prefix and the next free number, then re-sort. Dropdowns and Summary formulas already cover rows 2 to 400.
Re-sorting | Row order is the recommended work sequence, not a deadline sort. Check Depends on before starting; other team members may own prerequisites. Status is maintained separately in the online tracker.
Week colours | Column A is the solid chip; the rest of the row is the same hue at 22 per cent, which keeps text contrast above 6.9 to 1
Sep W1 | #264653 row tint #CFD6D9
Sep W2 | #287271 row tint #D0E0E0
Sep W3 | #2A9D8F row tint #D0E9E6
Sep W4 | #8AB17D row tint #E5EEE2
Oct W1 | #E9C46A row tint #FAF2DE
Oct W2 | #F4A261 row tint #FDEBDC
Oct W3 | #EE8959 row tint #FBE5DA
Oct W4 | #E76F51 row tint #FADFD9
Column | Meaning
Target week | The week this should be finished. Change it and the row colour when a task slips, or the colours stop telling the truth.
Wk | Week number 1 to 8, used for sorting. 1 is September W1.
ID | Category prefix plus a number. Stable: never renumber, because Depends on points at these. Re-sorting never changes an ID, which is the point of having them.
Category | Type of work. The ten categories agreed for this project.
Task | One deliverable, small enough for one person to finish inside a week.
Scope ref | Which numbered item in section 4.1 (In scope) or section 8 (Methodology) of the proposal this satisfies. Every scope item should appear at least once.
Owner | One name. Two owners means nobody owns it. Dropdown reads the People sheet.
Status | To do, Doing, Blocked, Done. Blocked is not a synonym for To do: it means another task must finish first, and Notes should say which.
Priority | P0, P1, P2. Defined below. Inside a week, clear the P0 block before P1.
Depends on | IDs that must reach Done before this can start. This column, not the week, is what actually determines order. A task whose dependency sits in a later week is a planning error: fix it when you see it.
Est (days) | Person-days of real work, not calendar days. An estimate you know is optimistic is worse than no estimate.
Privacy check | Yes means the task touches stored personal data or sends data abroad, shown in bold teal. A Yes task is not Done until the three PDPA rules below hold.
Definition of done | The observable condition that ends the task. Written before starting.
Notes | Blockers, decisions, PR links.
Priority | Meaning
P0 | On the critical path. Something else cannot start until this is done, or the demo cannot be shown without it. Slipping a P0 slips the project.
P1 | Required by the proposal scope but blocking nobody. Slipping it costs completeness, not the schedule.
P2 | Cuttable. Section 8.6.2 names the cut order: the language model first, because the Thai template is already a complete answer, then OCR, because manual entry is a full alternative.
PDPA rules | Apply to every task whose Privacy check is Yes
Rule 1 | If the code path writes student data, it checks the storage consent flag first and stores nothing without it (In scope 23).
Rule 2 | If the code path sends data outside Thailand, it checks the separate cross-border flag and falls back to the Thai template (In scope 24, 25).
Rule 3 | If a payload leaves the system, it carries only anonymised numeric values: no name, LINE user id, course id, or individual component score (In scope 26).
Example row | How a filled row should look
Sep W2 ¦ 2 ¦ ENG-03 ¦ Engine ¦ Minimum required score on remaining assessments ¦ In scope 10 ¦ Nan ¦ Doing ¦ P0 ¦ ENG-02 ¦ 1.0 ¦ No ¦ Matches the RogerHub formula on three hand-checked cases ¦ branch feat/required-score, PR #14